## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (actual date) | Date finished (actual date)
1 | Import data in text file format | As a user, I want to import data in text file format so that I can enhance my workflow and improve overall efficiency. | high | sprint1 | 1. Users can successfully complete the import data in text file format process. 2. The system provides feedback and necessary validations. 3. Users can undo or modify actions where needed. | 2 | Primary requirement | 20250320 | 20250322
2 | Automatic entry of transaction data by the user | As a user, I want to automatically add my transactions first, if some mistakes, then I could manually enter my transactions, so that I can keep a detailed record of my expenditures quickly. | high | sprint1 | 1. Users could choose automatic transaction entry or manual transaction entry. 2. If automatic, the app should read all user's data and save them automatically with proper sorting. 3. Finally, The system saves the data correctly. 4. Users could modify data at any time. | 5 | Primary requirement | 20250322 | 20250327
3 | Manual entry of transaction data by the user | As a user, if some mistakes when automatic transaction, I could manually enter my transactions, so that I can keep a detailed record of my expenditures whenever automatic entry makes any mistakes. | high | sprint1 | 1. Users could choose automatic transaction entry or manual transaction entry. 2. If manual, Users are able to enter transaction information such as date, amount, category, etc, and completely personally specified. 3. Finally, The system saves the data correctly. 4. Users could modify data at any time. | 3 | Primary requirement | 20250327 | 20250330
4 | Manual Classification of Transactions | As a user, I can manually categorize my income, expenses and transactions according to my preferences. | high | sprint2 | 1. Manual classification by users: Users can define the personal definition in their transaction records. 2. Multi-dimensional statistics: Classified data should support multi-dimensional summaries by time, type, card account, etc., and generate visual charts (such as bar charts showing expenditure proportions). 3. Historical report data is automatically updated to avoid inconsistent statistics due to category changes. 4. All classification operations must be recorded in operation logs, and users can view modification histories and the operators (such as "User changed 'Dining' to 'Entertainment' on 2025-03-17"). | 5 | Primary requirement | 20250401 | 20250405
5 | AI Automated Classification of Transactions | As a user, I can also let the AI help me do the categorization automatically, so that I can manage my wealth both according to my own preferences and have the AI assist me in implementing it quickly. | high | sprint2 | 1. AI automatic classification: AI automatically classifies transactions, and users can correct the AI's classification. User-defined sorting takes the highest priority. 2. Multi-dimensional statistics: Classified data should support multi-dimensional summaries by time, type, card account, etc., and generate visual charts (such as bar charts showing expenditure proportions). 3. Historical report data is automatically updated to avoid inconsistent statistics due to category changes. 4. All classification operations must be recorded in operation logs, and users can view modification histories and the operators (such as "User changed 'Dining' to 'Entertainment' on 2025-03-17"). | 4 |  | 20230406 | 20250410
6 | User manually modifies the AI classification | As a user, I want to manually adjust AI-classified transactions to ensure accuracy and align with my preferences. | medium | sprint2 | 1. Users can view AI-classified transactions and make modifications. 2. Users can save changes and have the system reflect them immediately. 3. The system logs and tracks all manual modifications for audit purposes. | 3 |  | 20250411 | 20250414
7 | Users can view their account information | As a user, I want to have access to my change, monthly expenses and income, historical transactions, card information, and weekly income summary at all times,and also I could add new cards, so that I can keep track of my wealth. | high | sprint3 | 1. The system must aggregate and display the following data: changeable pocket money, monthly income and expenditure, historical transactions, card information, weekly income summary (in the form of charts and graphs for visualization). 2. Data synchronization timeliness: automatic synchronization or support for users to manually refresh, support for users to modify historical transaction records. 3. Support for users to interactively view details and export reports. | 7 |  | 20250415 | 20240422
8 | Analysis of consumption trends | As a user, I want to analyze my consumption trends over time, so that I can identify patterns, make budget adjustments, and improve my financial management. | high | sprint3 | 1.The system provides visual charts and graphs to display consumption trends (e.g., monthly spending, category-wise spending). 2.Users can filter and view trends by different time periods (e.g., daily, weekly, monthly, yearly). 3.Users can export trend analysis reports in various formats (e.g., PDF, Excel). 4.The system logs all trend analysis activities for future reference. | 2 |  | 202500423 | 20250425
9 | AI provides consumer advice | As a user, I want the AI to analyze my spending patterns and provide personalized consumer advice, so that I can make more informed financial decisions and optimize my spending habits. | high | sprint3 | 1.The AI analyzes historical transaction data to identify spending patterns and trends. 2.The system generates personalized advice based on user spending behavior 3.Users can view and interact with the advice provided by the AI. 4.The advice is updated regularly based on new transactions and user feedback. 5.The system logs all AI-generated advice and user interactions for future reference. | 3 | together with story 8 | 20250425 | 20250428
11 | Generate financial reports | As a user, I want to generate comprehensive financial reports, so that I can analyze my financial trends, track progress towards financial goals, and make informed decisions. | low | sprint3 | 1.The system provides options to generate various financial reports. 2.Users can customize the content and format of the reports. 3.The system provides visual charts and graphs to enhance report readability. 4.Users can export reports in different formats. 5.The system logs all report generation activities for future reference. | 1 |  | 20250429 | 20250430
10 | Smart Budget Reminder | As a user, I want to receive smart budget reminders based on my spending habits and budget limits, so that I can stay within my budget and avoid overspending. | medium | sprint4 | 1.The system allows users to set budget limits for different categories. 2.The system sends reminders when spending approaches or exceeds the set budget limits . 3.Users can customize the frequency and format of budget reminders . 4.The system adjusts reminders based on user feedback and spending patterns. 5.The system logs all budget reminders and user interactions for future reference. | 5 |  | 20250506 | 20250511
12 | Multi-card management | As a user, I want to manage multiple financial card accounts in one place, so that I can get a holistic view of my finances and easily track transactions across different accounts. | low | sprint4 | 1.The system allows users to link multiple financial card accounts. 2.Users can view transactions and balances for all linked acrd accounts in a unified dashboard. 3.The system provides options to categorize and analyze transactions across multiple card accounts. | 2 |  | 20250512 | 20250514
13 | Data privacy protection | As a user, I want my financial data to be protected with robust privacy measures, so that I can trust the system with sensitive information and avoid unauthorized access. | high | sprint4 | 1.The system implements industry-standard encryption for data storage and transmission. 2.Users can control access to their data through customizable privacy settings . 3.The system provides regular security updates and patches to protect against vulnerabilities. 4.Users receive notifications of any security incidents or data breaches. | 3 |  | 20250515 | 20250518
14 | Currency interoperability among different countries and regions | As a user, I expect the system to automatically switch the currency unit according to the exchange rate, so that I can use this app anywhere on the earth. | low | sprint4 | 1. The system must be able to select the main currency either based on the user's geographical location (via GPS or IP positioning) or through manual selection. 2. Once the currency is switched, other data should be synchronized and switched accordingly, and presented accurately. | 1 |  | 20250519 | 20250520